## Feuille 1
ISSUE # | User Story/Task Title | Story Points | Due Date | Associated Tasks/Task Description | Priority | Risk | Responsible
SPRINT I |  |  | 2025-02-07
1 | US#1 As an user, I want to be able to create an account where I will be able to use my username and password to log in afterwards. | 3 | 31.1 | Implement register form Create new supabase user with form information | !! | high | Steven/Mai
2 | US#2 As an user, I want to be able to log in with my username and password so that I can access my personal data and communication channels. | 3 | 31.1 | Create login form Link to supabase backend to authenticate user Show test message to show user is logged in | !!! | med | Steven/Mai
3 | US#3 As an user, I want to be able to know which role (admin or member) I possess so that I can understand what privileges I have within the app. | 1 | 3.2 | Create roles table in supabase Add role fetching to login functionality Output user role once in dashboard | !! | low | Haytham
5 | US#4 As an user, I want to be able to view available channels so that I can participate in group discussions. | 2 | 6.2 | Add channels table in supabase Add user channel fetching in login Output channels related to user id from database | !!! | med | Shayaan/Mohamed
6 | US#5 As an user, I want to be able to view which other members are within a channel so that I know who I can communicate with. | 2 | 6.2 | Retrieve all user ids from one channel from supabase Output all ids | ! | med | Shayaan/Mohamed
7 | US#6 As an user, I want to be able to leave text channels I've joined so that I can stop receiving messages from that group. | 1 | 6.2 | Create frontend button to leave channel Update supabase table to delete row from users_channels | ! | high | Shayaan/Mohamed
8 | US#7 As an user, I want to be able to logout of my account so that I can protect my data when I'm away. | 1 | 3.2 | Create frontend button to logout Use supabase authentication to securely logout user from session | !!! | low | Steven/Mai
9 | US#8 As an admin, I want to be able to create and name channels so that I can organize different discussion topics. | 2 | 3.2 | Create frontend form for channel creation Create supabase policies for admins only Add supabase row in channels table with criteria specified | !!! | high | Mohamed/Haytham
10 | US#9 As an admin, I want to be able to manage (delete) inappropriate channels so that I can maintain a safe environment. | 1 | 3.2 | Create frontend button to remove channels Create supabase policies for admins only Delete supabase row in channels table | !! | med | Mohamed/Haytham
11 | US#10 As an admin, I want to be able to assign members to channels so they can participate to the topic. | 2 | 6.2 | Create frontend button to add users to channels Create supabase policies for admins only Add row in users_channels table in supabase | !!! | med | Mohamed/Haytham
12 | US#11 As an admin, I want to be able to remove users from channels if needed so that I can moderate group discussions effectively. | 1 | 6.2 | Create frontend button to remove users from channels Create supabase policies for admins only Delete row in users_channels in supabase | !! | low | Mohamed/Haytham
13 | US#12 Submit meeting minutes | 1 | 6.2 | Post on Github meeting minutes | !!! | low | Hala
19 | US#13 Submit README file | 1 | 4.2 | Post on Github README file | !!! | low | Hala
23 | US#14 As a user, I want to be able to view the homepage so that it's easier to navigate the software | 2 | 4.2 |  | !! | med | Hala
27 | US#15 Submit project planning | 1 | 6.2 | Post on Github project planning | !!! | low | Haytham/Mai
SPRINT II
29 | US#16 As a user, I want to be able to send and receive direct messages to other users. | 4 | 7.3 | Implement backend messaging logic Ensure Encryption and Security Implement Real-Time Message Updates Implement UI for Selecting a Friend to DM | !!! | high | Steven/Mai/Hala
33 | US#17 As a user, I want to be able to send and receive messages in text channels to communicate with multiple users. | 6 | 7.3 | Implement Backend for Sending and Storing Channel Messages Implement UI for Sending and Displaying Channel Messages Implement Admin Message Moderation (Delete Feature) Implement Real-Time Updates for Channel Messages | !! | high | Mohamed/Haytham/Shayaan
45 | US#18 Submit meeting minutes | 1 | 7.3 |  | ! | low | Hala
| US#19 Project Documentation | 1 | 7.3 |  | ! | low | Haytham
SPRINT III
SPRINT IV